## Slide 1: Social differentiation
  Outcome: Knowing sustainable agriculture and food security in the context of climate change (now & future) through better decision making. This requires recognition and action on social differentiation, which can be enabled through the use of social learning.
  Rationale: Decision making on future food security and climate change at the local level (communities and other groups) is not inclusive and equitable, which is not optimal. Social learning will allow us to understand and address social differentiation while providing evidence and action.

## Slide 2: Social differentiation
  ACTIVITY 1 – Catalyzing Change from Within (2012 – 2013)
    Lead: CCAFS Theme 4
    Target Audience: CCAFS & current project partners
      Internal review of CCAFS/CG to look for opportunities to further social differentiation and developing strategy for augmenting this work through developing a social learning process.
      Use baseline work to analyze social differentiation, findings from PAR work
      Linking social learning process to its annual Science Meeting
      Create working group with CCAFS and experts on social learning and differentiation
        (Social LSD)
  ACTIVITY 2 – Facilitation (2012 – 2020)
    Lead: Social LSD
    Develop a dynamic network cutting across Social LSD
    Identify ways to coordinate & facilitate the process
    Organize a working group to lead Activity 3

## Slide 3: Social differentiation
    ACTIVITY 3 - Global Action Research Agenda on Social LSD in CC,A, FS (2012-2013)
    Audience: Climate change and food security community in CCAFS countries
    (a) Phase 1 – Developing a research agenda (loop 1): Facilitate social learning process to devise research agenda. Phase 1 will help to provide evidence, identify partnership, better understanding, principles, rigorous methodology, and communities of practice. This will also include linking practioners with researchers. This process will:
      Use crowd sourcing
      Produce literature review on existing work
      Conduct scoping process (activities at sub-national level) to help create a research framework
      Generate a bucket of tools and approaches on to conduct research on social learning and differentiation
      Develop a framework and principles on conducting social learning and differentiation, including action research
      Fund initial proposals through a call on social learning and differentiation
    (b) Phase 2 (loop 2): Research to action 2014-2020
      Iterative process of learning as research underway – e.g. Online forum; Wiki; annual workshops; publication
      Capacity development on methodology and approach within the CG system and beyond
      Demonstrate the evidence
      Move towards impact with partners
  Funding ballpark:
    Activity 1 & 2: $50,000
    Activity 3: $300,000